## Budget Status Q1
Meridian Cultural Center — Budget Status
As of March 10, 2026
Category | Amount | Notes
Total approved budget | 4200000
EU Recovery Fund (70%) | 2940000 | Grant expires Dec 31, 2026
City co-financing (30%) | 1260000
Spent to date | 910000
Committed (signed contracts) | 2180000
Remaining uncommitted | 1110000
Contingency reserve (original) | 300000
Used — design changes | 120000 | Approved Nov 2025
Used — emergency structural assessment | 22000 | Feb 2026 — not in original PM handover docs
Contingency remaining | 158000
Asbestos remediation (provisional) | 200000 | (*) Preliminary estimate — visual inspection only (Jan 2026)
(*) NOT approved. NOT committed. NOT deducted from contingency. Final estimate pending.
Note: If asbestos remediation costs exceed remaining contingency, a formal budget modification
request must be submitted to City Council. Approval process: 4-6 weeks.
Prepared by: Marta Vidal, Budget Controller, City Finance Department